## Sprint 1
Functional Testing Case Study - 1
Task/Scenario Given: |  | The following website is given for Manual Testing to follow Agile practices and design and execute Test Cases and create Defect Report https://unacademy.com/
Sprint Day | Sprint Activity | Overview and scope of functionality
Sprint Day 1 | Project Management Activity: Product Owner 1. Create user stories based open functionality I. Understanding requirements II. Assign priority III. Assign user stories to team members 2. Identify the Dependacy between the requirement 3. Final ordering of product backlog item( set of all user stories) Create Task / Deliverables: 1. List of User Stories & Functions to test 2. All tasks with JIRA should be ready in SCRUM template | Project Overview: Unacademy is India’s largest, online learning platform. It allows educators to create courses on various subjects. and more on thousands of internet-connected devices. With Unacademy, students can watch unlimited ad-free viewing of our study content In scope Functionality: 1)Signing in 1. Once you've opened the Unacademy app or Unacademy website, select Sign In to access your account and begin accessing exam material and videos. The 'Sign In' button directs the user to the 'Sign In' page where the user needs to enter the credentials viz. the registered email or phone number and its corresponding password. 2. You can sign in on any Unacademy-compatible device, or on multiple compatible devices. 3. If the user is a first-time visitor and does not have an account, they have the option to sign up for the same and avail further services. 2)Start Learning A 'Start Learning' link is also present if someone doesn’t understand what to do next. The link redirects the user to the page where different exam modules are present 3) Search There is an option of Searching in which user can search Trending Educators and after clicking on educator name, user redirect to the respective educator profile page.. 4)About Us The About Us link gives general information about the websites 5)Get Subscription This option can be used to : 1. To view Plan and monthly cost 2. View your billing Date 3. Update your payment information 4. Print your Unacademy information Out of Scope Functionality: 1Load testing, Localization Testing, Volume Testing Expected Implementations : 1. Usage of all Testing Types 2. Usage of Test Design Techniques like EP, BVA etc. 3. Usage of Valid invalid input data 4. Test case design in Integration and system level testing
Sprint Day 2 | JIRA Task and Test Design : Dev Team 1. Assign story point or time required to accomplish the story/Task 2. Categorize user stories in to Epic, User Stories, Tasks & SubTasks 3. Assign the stories to components 4. Add group members in th Project on JIRA. 5. Create MAnual Test Scenarios Create Task / Deliverables: 1. Test scenarios 2. Test Case design
Sprint Day 3 | Scrum Team activities : Dev Team 1. Create scrum based sprints 2. Create Sprint backlog (select the stories for the particular Sprint) 3. Create Sprint board (Todo , in process, Done) Create Task / Deliverables: 1. Test Case design 2. Test Case execution
Sprint Day 4 | Scrum Team Activity : Scrum Team (PO, SM, DT) 1. Plan for release 2. Generate Agile report relevant to scrum project (e.g. Burn down chart, Sprint report etc.) Create Task / Deliverables: 1. Defect reporting 2. Traceability Matrix 3. Test summary report Keep all the Deliverables on Git
Sprint Day 5 | Sprint Evaluation

## User Stories
Issue Type | Summary
Epic 1 | Signing in
| Story 1 | Any Registered user can sign in to subscribe for any course,receive notification mails ,track his/her classes and change account settings.
| Story 2 | Any Unregistered user should be able to sign in to subscribe for any course,receive notificationmails ,track his/her classes and change account settings.
Epic 2 | Get Subscription
| Story 1 | Any registered user or an unregistered user can subscribe to any course, view different plans according to the monthly cost.
| Story 2 | Any registered user should be able to choose between different payment methods and input the required valid details to complete the payment procedure. An unregestered user should be directed to Sign in page before payment.
| Story 3 | Any registered user should be able to view the billing dates whenever required using the 'Get subscription" button.
| Story 4 | Any registered user should be able to update and view payment information.
| Story 5 | Any registered user should be able to view and print Unacademy information whenever required using the 'Get subscription" button.
Story 1 | Start Learning
Any Registered/Unregistered User can click on 'Start Learning' to get options on different Exam Modules and the corresponding courses offered.
Story 2 | Search
Any registered or unregistered user can search for different courses, lessons and educators on the search bar according to his/her preference.
Story 3 | About us
Any Registered/Unregistered User can click on 'About Us' and view details about unacademy such as team members and company.

## Test Case Template
Test Case ID | Test Scenario | Precondition | Test Condition | Test Case Steps | Test Data | Expected Result | Actual Result Iteration 1 | Status Iteration 1 | Actual Result Iteration 2 (to be updated only if test case failed in Iteration 1) | Status Iteration 2 (to be updated only if test case failed in Iteration 1) | Comments | Req: Reference
TC_SubB_001 | Verify fuctionality of Subscription page | url https://unacademy.com/ should be working | To verify working of Get subscription button | 1.Choose any desired course 2.Click on "Get subscription" button | UPSC CSE-GS | A new page should be displayed showing subscription plans | A new page should be displayed showing subscription plans | Pass
TC_SubB_002 |  | url https://unacademy.com/ should be working | To verify working of Subscription plan page | 1.Choose any desired course 2.Click on "Get subscription" button | Railway Exams | Page should display different subscription plans along with checkboxes for the user to select and a "Proceed to Pay" button at the bottom | Page should display different subscription plans along with checkboxes for the user to select and a "Proceed to Pay" button at the bottom | Pass
TC_Pay_001 | Verify fuctionality of Proceed to Pay button | url https://unacademy.com/ should be working | To verify working of Proceed to Pay button for a registered user | 1.Choose any desired course 2.Click on "Get subscription" button 3. Choose a suitable subscription plan 4.Click on "Proceed to pay" | Railway Exams Subscription 3 months | A new page should appear displaying different payment methods | A new page should appear displaying different payment methods | Pass
TC_Pay_002 |  | url https://unacademy.com/ should be working | To verify working of Proceed to Pay button for an unregistered user | 1.Choose any desired course 2.Click on "Get subscription" button 3. Choose a suitable subscription plan 4.Click on "Proceed to pay" | Railway Exams Subscription 3 months | A new page should appear displaying different payment methods and the unregistered user should be directed to create an account | A new page should appear displaying different payment methods and the unregistered user should be directed to create an account | Pass
TC_Part_001 | Verify payment in part method | 1.url https://unacademy.com/ should be functioning 2.User should be a registered user. | To verify working of payment in parts method | 1.Click on "Proceed to pay" 2.Click on "Continue" 3.Choose any part option 4.Click on "Next" and choose any payment method and fill the valid details 5.Enter valid referral code if any 6.Click on "Pay" | 2 part | It should display "Payment Successful" along with payment details and an option to print this information. | It should display "Payment Successful" along with payment details and an option to print this information. | Pass
TC_Card_001 | Verify payment using Card | 1.url https://unacademy.com/ should be functioning 2.User should be a registered user. | To verify payment using valid card details | 1.Click on "Proceed to pay" 2.Choose Cards 3.Enter valid card number 4.Enter valid expiry date 5.Enter valid CVV 6.Enter name on the Card 7.Enter valid referral code if any 8.Click on "Pay" | Card no :xxxx xxxx xxxx xxxx Expiry date:2/26 CVV: xxx Name:ABC | User should be able to follow the required steps for payment using Card and successfully complete the payment. | User should be able to follow the required steps for payment using Card and successfully complete the payment. | Pass
TC_Card_002 |  | 1.url https://unacademy.com/ should be functioning 2.User should be a registered user. | To verify payment using invalid card details | 1.Click on "Proceed to pay" 2.Choose Cards 3.Enter invalid card number 4.Enter invalid expiry date 5.Enter invalid CVV 6.Enter name on the Card 7.Enter valid referral code if any 8.Click on "Pay" | Card no :xxxx xxxx xxxx Expiry date:24/26 CVV: xx Name:ABC | It should block clicking on "Pay" button | It should block clicking on "Pay" button | Pass
TC_Card_003 |  | 1.url https://unacademy.com/ should be functioning 2.User should be a registered user. | To verify payment using card and by keeping few fields blank | 1.Click on "Proceed to pay" 2.Choose Cards 3.Enter card number 4.Enter valid expiry date 5.Enter valid CVV 6.Enter name on the Card 7.Enter valid referral code if any 8.Click on "Pay" | Card no :-- Expiry date:2/26 CVV: xxx Name:--- | It should block clicking on "Pay" button | It should block clicking on "Pay" button | Pass
TC_Net_001 | Verify payment using Netbanking | 1.url https://unacademy.com/ should be functioning 2.User should be a registered user. | To verify payment using Netbanking method | 1.Click on "Proceed to pay" 2.Choose Netbanking 3.Choose your Bank 4.Enter valid referral code if any 5.Click on "Pay" | HDFC Netbanking | It should display the bank page asking for valid credentials and user should be able complete the payment following the required steps in Netbanking method. | It should display the bank page asking for valid credentials and user should be able complete the payment following the required steps in Netbanking method. | Pass
TC_UPI_001 | Verify payment using UPI | 1.url https://unacademy.com/ should be functioning 2.User should be a registered user. | To verify payment using valid UPI credentials | 1.Click on "Proceed to pay" 2.Choose UPI 3.Enter valid UPI ID 4.Enter valid referral code if any 5.Click on "Pay" | xxxxxxxxxx@okicic | A new page should appear for processing the transaction , a user should be a able to successfully in payment procedure. | A new page should appear for processing the transaction , a user should be a able to successfully in payment procedure. | Pass
TC_UPI_002 |  | 1.url https://unacademy.com/ should be functioning 2.User should be a registered user. | To verify payment using invalid UPI credentials | 1.Click on "Proceed to pay" 2.Choose UPI 3.Enter invalid UPI ID 4.Enter valid referral code if any 5.Click on "Pay" | xxxxxx@abd | It should display "Transaction failed" | It should display "Transaction failed" | Pass
TC_UPI_003 |  | 1.url https://unacademy.com/ should be functioning 2.User should be a registered user. | To verify payment by keeping UPI ID field balnk | 1.Click on "Proceed to pay" 2.Choose UPI 3.Enter UPI ID 4.Enter valid referral code if any 5.Click on "Pay" | __ | It should block clicking on "Pay" button | It should block clicking on "Pay" button | Pass
TC_Wall_001 | Verify payment using Wallets | 1.url https://unacademy.com/ should be functioning 2.User should be a registered user. | To verify payment using valid Wallet credentials | 1.Click on "Proceed to pay" 2.Choose Wallets 3.Choose a wallet 4.Enter valid phone number 5.Enter valid referral code if any 6.Click on "Pay" | xxxxxxxxxx | Respective Wallet page should appear which will require user to enter credentials for successful payment. | Respective Wallet page should appear which will require user to enter credentials for successful payment. | Pass
TC_Wall_002 |  | 1.url https://unacademy.com/ should be functioning 2.User should be a registered user. | To verify payment using invalid Wallet credentials | 1.Click on "Proceed to pay" 2.Choose Wallets 3.Choose a wallet 4.Enter invalid phone number 5.Enter valid referral code if any 6.Click on "Pay" | xxxxxxx | It should block clicking on "Pay" button | It should block clicking on "Pay" button | Pass
TC_Wall_003 |  | 1.url https://unacademy.com/ should be functioning 2.User should be a registered user. | To verify payment by Wallets method , keeping phone number blank | 1.Click on "Proceed to pay" 2.Choose Wallets 3.Choose a wallet 4.Enter phone number 5.Enter valid referral code if any 6.Click on "Pay" | ___ | It should block clicking on "Pay" button | It should block clicking on "Pay" button | Pass
TC_EMI_001 | Verify payment using EMI | 1.url https://unacademy.com/ should be functioning 2.User should be a registered user. | To verify payment using EMI method | 1.Click on "Proceed to pay" 2.Choose EMI 3.Choose a EMI Plan 4.Enter valid details 5.Click on "Next" 6.Enter valid referral code if any 7.Click on "Pay" | ____ | User should be able to follow the required steps for payment using Card and successfully complete the payment. | User should be able to follow the required steps for payment using Card and successfully complete the payment. | Pass
TC_Ref_001 | Verify for valid referral code | 1.url https://unacademy.com/ should be functioning 2.User should be a registered user. | To verify use of valid referral code | 1.Click on "Proceed to pay" 2.Choose a payment option 3.Enter the required credentials 4.Enter valid referral code if any 5.Click on redeem | abcde | It should display the amount of discount earned by the user. | It should display the amount of discount earned by the user. | Pass
TC_Ref_002 |  | 1.url https://unacademy.com/ should be functioning 2.User should be a registered user. | To verify use of invalid referral code | 1.Click on "Proceed to pay" 2.Choose a payment option 3.Enter the required credentials 4.Enter invalid referral code if any 5.Click on redeem | zz//zz | It should display "Please enter a valid code" | It should display "Please enter a valid code" | Pass
TC_Ref_003 |  | 1.url https://unacademy.com/ should be functioning 2.User should be a registered user. | To verify validity of referral code. | 1.Click on "Proceed to pay" 2.Choose a payment option 3.Enter the required credentials 4.Enter valid referral code if any 5.Click on redeem | CAT10 | It should display code has been expired. | It displays the referral code has been applied and redeemed successfully | Fail
TC_Upd_001 | Updating Payemtn Information | 1.url https://unacademy.com/ should be functioning 2.User should be a registered user. 3. User should have subscribed for a course | To verify for updating payment information | 1.Click on "Get Subscription" 2.Click on Update Payment Information | ___ | User should be able to update the payment information | User should be able to update the payment information | Pass

## Test Scenario
TestScenarioID | Requirement ID | UserStory | Test Scenario Description | Type of testing | Possible no of test Cases | Test Case Details
TS_SubB | UN-9 | Get subscription for user | To verify fuctionality of Subscription page | UI | 2 | 1.Verify working of "Get Subscription" button. 2.To verify Subscription plans page
TS_Pay |  |  | To verify fuctionality of Proceed to Pay button | Functional | 2 | 1.To verify functionality of Proceed to Pay button for a registered user 2.To verify functionality of Proceed to Pay buttonfor an unregistered user
TS_Part | UN-11 | Payment methods | To verify payment in part method | Functional | 1 | To check working of payment in parts method
TS_Card |  |  | To verify payment using Card | Functional | 3 | 1.To verify successful payment using valid card details 2.To verify successful payment using invalid card credentials 3.To verify payment by card , keeping some of the credentials filed empty
TS_Net |  |  | To verify payment using Netbanking | Functional | 1 | To verify successful payment using Netbanking method
TS_UPI |  |  | To verify payment using UPI | Functional | 3 | 1.To verify successful payment using valid UPI ID 2.To verify successful payment using invalid UPI ID 3.To verify payment by UPI method, by keeping the field empty
TS_Wall |  |  | To verify payment using Wallets | Functional | 3 | 1.To verify successful payment using valid phone no 2.To verify successful payment using invalid phone no 3.To verify payment by Wallets method, by keeping the field empty
TS_EMI |  |  | To verify payment using EMI | Functional | 1 | To verify successful payment using EMI method
TS_Ref |  |  | To verify for valid referral code | Functional | 3 | 1.To verify use of valid referral code 2.To verify use of invalid referral code 3.To verify validity of refferal code
TS_Upd | UN-17 | Updating Payemtn Information | To verify for updating payment information | Functional | 1 | To check working of Update Payment Information

## Reports
Reports
Burndown Chart
Sprint Report

## Defect Report
Defect Id. | Module name | Defect Summary | Defect Priority | Assigned To | Status
UN-19 | Payment methods | Payment methods_ expired referral code should not be accepted | High |  | To do

## Test Summary
Test Summary Report
Sr.No | Activities | Count | Passed | Failed
1 | Created User Stories | 10
2 | Created Test Cases | 43
3 | No of Test Cases executed in Sprint1, Iteration1 | 43 | 39 | 4
4 | Defects Reported | 4
Any Challenges
Website isn't user friendly

## Sprint 2
Automation Testing Case Study - 1
Following website is given for Automating Testing using Selenium Automation Page Factory/POM, TestNG & BDD Framework (using Cucumber)
Url: http://demowebshop.tricentis.com
Sprint Day # | Task / Scenario Given | Deliverables at the EoS Day#
Sprint Day 1 | 1. Java Case study completion individually | 1. Case Study implementation code
| 2. Identify the Manual Test Cases that you want to automate. | 2. Test Cases: Positive & Negative
| 3. Plan the flow of application that you want to test using automation test scripts. | 3. Application Flows: Positive & Negative.
| 4. Create a Maven Project - Associate required libraries with the Maven Project | 4. Creation of project structure
5. Configure required dependencies like Selenium WebDriver, TestNG / Junit, Cucumber etc. in POM.xml
Sprint Day 2 | 1. Create the required Feature files with relevant scenarios (User Stories) using Gherkin. | 1. List of Feature Files :
| · Use Scenario Outline & Examples to implement Parametrization in Feature File | 2. List of Test Cases :
| 2. Implement Page Factory or Object Repository (XML/Property File) to identify and store all the web elements. | 3. Prioritization of tests :
| · Use all types of Locators | 4. Parametrization Sample Data :
| · Ensure appropriate usage of Selenium Web Driver API objects and import statements | 5. Any Test Suite?
| 3. Implement parametrization using apache POI | 6. Test Runner class Parameters
| 4. Implement TestNG for generating reports and XML file for parallel execution of test suite | 7. Report File Names
5. Design the test runner class
Sprint Day 3 | 1. Generate Step Definitions and write the Tests addressing all the functional requirements. | 1. Detail Test Script in Step Definitions
| · Implement Assertions/Verifications using TestNG | 2. Feature File- Test Case – PF/OR collation in an Excel sheet
· Use appropriate wait statements
· Handle new windows, popup’s, navigations
2. Ensure implementation of good programing practices
· Variable, Function & procedure naming convention
· Usage of comments
· Code Indentation
Sprint Day 4 | 1. Generate Traceability Matrix based on Feature File User Stories, Test Scripts and Defects | 1. Traceability Matrix
| 2. Finally generate TestNG/XML Test report mentioning pass/fail status. | 2. Test Reports
| 3. Keep all code in Git repository | 3. Final execuatble code in Git
Sprint Day 5 | 1. Jenkins Implimentation 2. Project Closure | 1. Create build using Jenkins
Sprint Day 6 | Sprint Evaluation